## Cover
Shiftbase Support Tickets
10 tiket simulasi + 2 insiden nyata (T-001, T-002)

## Tickets
ID | Judul | Severity | Status | Opened | Closed | Timeline | Diagnosis | Resolusi | Pencegahan
T-001 | Bind 8080 bentrok dengan API live lain | Medium | Closed | 2026-09-15 | 2026-09-15 | 1. compose up gagal bind 0.0.0.0:8080 2. ss: dipakai live lifeos 3. Override port via !override (merge tak cukup) 4. Stack Up di 18093/18094/13309 | Port host bentrok (matrix | Override file dengan !override + port alternatif | Cek ss sebelum up; !override bukan merge untuk ports
T-002 | Backup/restore roundtrip MySQL | High | Closed | 2026-09-15 | 2026-09-15 | 1. mysqldump lokal tak ada (pakai shim docker exec) 2. Env MYSQL_PWD tak terus ke docker exec (2x gagal) 3. Roundtrip: 5 employees + 3 users kembali | Tooling + env forwarding (matrix backup/restore) | Shim teruskan -e MYSQL_PWD; skrip lolos roundtrip | Dokumentasikan kebutuhan mysqldump; catat trik -e
T-003 | Seed ganda error 1062 | Low | Closed | 2026-09-15 | 2026-09-15 | 1. SOURCE seed.sql 2x 2. Duplicate admin@shiftbase.local 3. COUNT users = 3, skip | Seed tak idempoten (matrix | Tak perlu aksi | Cek COUNT sebelum seed
T-004 | Distroless tanpa shell saat debug | Low | Closed | 2026-09-15 | 2026-09-15 | 1. docker exec api sh gagal 2. Alih ke logs + adminer | Citra distroless by design (matrix | Prosedur debug tanpa exec | Tulis di runbook
T-005 | Check-in ganda 409 membingungkan user | Low | Open | 2026-09-15 |  | 1. User klik 2x 2. attendance_duplicate 3. UI sudah terjemahkan ke kalimat | Double-submit (matrix |  | Disable tombol saat request (usulan ke web)
T-006 | 401 massal setelah rotasi secret | Medium | Closed | 2026-09-14 | 2026-09-14 | 1. JWT_SECRET baru di-compose 2. Semua token hangus 3. Login ulang massal | By design (matrix | Komunikasi + login ulang | Umumkan rotasi sebelum deploy
T-007 | Import CSV header salah | Low | Closed | 2026-09-13 | 2026-09-13 | 1. User pakai header kapital 2. 400 + pesan header harus 3. Perbaiki header, sukses | Validasi ketat by design (matrix | Template CSV di FAQ | Sediakan file contoh
T-008 | Overtime 0 untuk shift 8 jam pas | Low | Closed | 2026-09-12 | 2026-09-12 | 1. Lapor: lembur tak muncul 2. Cek: durasi tepat 8 jam 3. Rumus GREATEST(jam-8,0) = 0 benar | Ekspektasi vs rumus (matrix | Edukasi definisi >8 jam | Tulis rumus di FAQ
T-009 | MySQL container tak healthy | Medium | Closed | 2026-09-11 | 2026-09-11 | 1. api restart loop 2. mysql starting (init 20 dtk) 3. depends_on healthy menahan api | Start order (matrix | Tunggu healthy; healthcheck sudah benar | Jangan bypass depends_on
T-010 | Data hilang setelah compose down -v | High | Closed | 2026-09-10 | 2026-09-10 | 1. down -v hapus volume 2. Restore dari backup harian 3. Data kembali | Flag -v destruktif (matrix | Restore + edukasi down vs down -v | Backup sebelum down -v; alias aman

## SLA
SLA compliance (COUNTIF hidup)
Metrik | Nilai
Total tiket | 10
Closed
Open
High severity
Closed rate